## Feuille 1
This document was produced within Task 6.3 of the TRIPLE project to support the organisation of the TRIPLE Open Science Training Series. It is part of the TRIPLE Training Toolkit deposited on Zenodo. DOI: 10.5281/zenodo.7309919 Authors: Tiziana Lombardo, Lottie Provost, Francesca Di Donato
The purpose of this spreadsheet is to support organisers, moderators and speakers in sharing the tasks related to the training sessions and to give a clear timeline. It also serves as a reference where the links relevant to the training session are copied in column E.
Last update: 10 November 2022.
INSERT DATE AND TITLE OF THE EVENT | For details see Guidelines
Task | Deadline | Resp. person | Status | Links/references | Involved team
Create zoom link |  |  |  | Add zoom link
Provide short description of the event to WP6
Duplicate template documents |  |  |  | Add link to the registration form
Send template slides to speaker
Upload description of the event on website (include registration link)
Create Email for partners to register (include registration link)
Create Invitation campaign on Mailchimp (include registration link)
Create Reminder campaign (x2) on Mailchimp
Create a Tag with the name of the event on Mailchimp
Create Mentimeter survey
Send Email to partners to register | 2 weeks before the event
Send Invitation campaign to potential participants via Mailchimp (send to the entire audience, include registration link) | 2 weeks before the event
Disseminate event on social media
Share the questions collected from the partners to the speaker (if any)
Import email adresses from the registration form in Mailchimp, tag them with name of the event.
Send Reminder campaign #1 via Mailchimp (use the tag of the event) | 2 days before the event
Final import of registered email adresses in Mailchimp, tag them with name of the event | on the day of the event
Send Reminder campaign #2 via Mailchimp (use the tag of the event) | on the day of the event
Update Mentimeter code on the speaker slides | on the day of the event
Start the session recording Important: make sure no one will use the zoom account at the same time | on the day of the event
Show the survey on mentimeter at the end of the session | on the day of the event
Keep track of number of attendees after the event | on the day of the event
Send speaker slides to WP8 leader (or WP6) to be stored on Zenodo, Nakala and Youtube
Send video recording to WP8 leader (or WP6) to be stored on Zenodo, Nakala and Youtube
Deposit your presentation (slides) in the dedicated folder in G-drive |  |  |  | Add link to the Google Drive folder
Store slides on Zenodo following the procedure designed by WP8
Download the data from the post-training survey on Mentimeter and and insert the data in the dedicated spreadsheet |  |  |  | Add link to a common spreadsheet which gathers all the data from pasrt surveys
Unsubscribe contacts who do not wish to receive future training events in Mailchimp
Create the learning resource on Dariah-Campus
Fill in WP8 documents on event planning and reporting
Update the project website with the links to video recordings, slides and Dariah Campus